## Sheet1
Edit | GIM | Issue Number | Module | Priority | Department | Responsible Name | Description | Station Description | Station | Method Of Discovery | Notes | Status | Create Originator Name | Open Date | Creation Date | Permanent Solution Description | AME Manager | AME Secondary Responsible | AME CreatedBy | AME Category | AME Severity | AME EPI TrackingNumber | VIN | Part Number | AME Simulation # | AMEDFA | AMEIssueCard | AMECCDDN | AMEEHPVReduction | AMETorqueDeviation | AMESanCode | Area Description | Reason | Permanent Solution Date | Manager Name | Closing Date | Tracking Number | Domain | Side | Secondary Responsible Name | PN | Chapter | Sub Chapter | Sub Chapter Class | Question | Question Description | Temporary Solution Date | Temporary Solution Required | Temporary Solution Description | Temporary Solution Approved | Temporary Solution Validated | Permanent Solution Validated | Subdepartment | Tech Contact Name | Solution Week | Historical Date | Status Date | WCM Pillar | Loop | LastUsername | lastTimeStamp | CreatedBy | VIN | Question PartNum | WhoMovedToP1 | WhenMovedToP1 | Line | Main Process Description | Subprocess Description | Category | 4M1D | Kaizen | Team | Parent Issue | Process Step | Initial RPN | Target RPN | Current RPN | RPN | QA Network | EPI | MPI | Severity | Detection | Occurence | Severity Target | Detection Target | Occurence Target | Severity Current | Detection Current | Occurence Current | Number Child | Model | Classification | Last Username Parent | Severity Parent | Detection Parent | Open Date Parent | Notes Child | Last Time Stamp Parent | Last Username Child | Last Time Stamp Child | Interim Corrective Action Date | Bringback Date
|  | 286192 | WPI | P2 | Safety | Gregory Bain | Amount of time the demask persons will be exposed to the isocyanates . | Paint Blank | PAINTBlank | WPI Layout Review | 4/13/2024 Corporate Industrial Hygienist John Rucinski has provided guidance. Everyone working in the demask booth is required to wear a PAPR (air purifying respirator, such as a Racal) due to the presence of Isocyanate. | Pending |  | 2024-03-07 08:43 | 2024-03-07 09:32 | Waiting on hygienist studies | [8 empty] | 0 | [5 empty] | 0 | Paint | Pending validation | 2024-09-30 |  |  |  | Paint 1 |  |  | 4 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 65 | 2024-04-15 |  |  | LOOP 0 | T3172SP | 2024-06-19T14:57:30.573+00:00 | Sulaiman Azeemuddin | [8 empty] | Method
|  | 286325 | WPI | P2 | Safety | Diana Tan | Training courses for hourly & salary to work in battery cell (pre - Launch requirements need to be defined) | Chassis Blank | ChassisBlank | PSR Installation Readiness Phase Checklist - Loop 3 | Diana Tan has created a matrix and is developing a plan on how to train prior to launch. Still in progress. | Pending |  | 2024-03-13 09:26 | 2024-03-13 09:00 | Working with CTC to allocate training for hourly to train prior to launching. This includes all online ESAFE courses as well in person training to allow operators to work with battery inside the battery cell. | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2025-06-23 |  |  |  | Chassis 1 |  |  | 7 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 103 | 2025-06-23 |  |  | LOOP 0 | T1766AG | 2024-05-01T12:06:46.61+00:00 | Abillan Gnanavel | [8 empty] | Man
|  | 286326 | WPI | P2 | Plant Facilities | Klaus Ohrnberger | Fire Suppression System upgrade (requirements /timing / budget) Above Battery Cell / Dock / Assembly to 9190 / BSR / CPA / Sim room | Chassis Blank | ChassisBlank | Build Issue | Many ongoing discussion regarding Fire Suppression - for X0 only sections of 9190 will be completed for pilot build. | Pending |  | 2024-03-13 09:24 | 2024-03-13 09:12 | In progress of bidding and finalizing layout for final layout to put cost estimations on. Lots of meeting going on to finalize this. Fire Suppression to be complete prior to launch. | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2025-02-03 |  |  |  | Chassis 1 |  | Douglas Grundy | 8 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE | Plant - Launch Team |  | 83 | 2025-02-03 |  |  | LOOP 0 | T1766AG | 2024-05-01T12:14:49.653+00:00 | Abillan Gnanavel | [8 empty] | Design
|  | 286437 | WPI | P3 | VPE IE | Prasad Madali | Digital scrolls need to be completed and converted to paper scroll in order to meet X0 pilot builds. For team leaders and operators to follow during the pilot build stage. Target date for X0- February 3rd, 2025 | Chassis Blank | ChassisBlank | Digital Scroll |  | Pending |  | 2024-03-14 12:32 | 2024-03-14 12:47 | Scrolls still in progress | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2024-12-18 |  |  |  | Chassis 1 |  |  | 11 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 76 | 2024-12-18 |  |  | LOOP 0 | T2851AD | 2024-05-24T13:24:55.5+00:00 | Anthony Dinardo | [8 empty] | Method
|  | 286633 | WPI | P3 | Safety | Gregory Bain | Safety Totem Requirements / Signage, Posters, and Restriction signs ready for the Battery Cell to restrict unauthorized/unqualified EE from entering. | Chassis Blank | ChassisBlank | PFMEA | Greg Bain and Steve Davis are working on totems for the Battery Cell - to be expected complete prior to X1. | Pending |  | 2024-03-22 11:37 | 2024-03-21 07:29 | This is a long term item. The totem will be placed at the entrance to the battery build area once that area is established | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2024-12-20 |  |  |  | Chassis 1 |  |  | 25 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 76 | 2024-12-20 |  |  | LOOP 0 | T1766AG | 2024-05-01T12:15:21.263+00:00 | Abillan Gnanavel | [8 empty] | Design
|  | 286792 | WPI | P2 | Weld Process Engineering | Omar Malik | Moving the door and fender cells away from delivery conveyers will eliminate the possibility of delivering panels to panel line via existing conveyors? | BIW Blank | BIWBlank | WPI Layout Review | 6/17/24: plan to compress panel line will eliminate the potential to reuse existing conveyors - final decision on panel line compression to be made in near future by senior mgnt. BAP + WPE are finalizing the business case to implement the reutilization of the delivery conveyors. Final buy-in and approval from WPE EE required | Pending |  | 2024-03-27 07:41 | 2024-03-25 21:35 | BAP + WPE are finalizing the business case to implement the reutilization of the delivery conveyors. Final buy-in and approval from WPE EE required | [8 empty] | 0 | [5 empty] | 0 | BIW | Pending validation | 2024-05-07 |  |  |  | Body 1 |  |  | 29 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 44 | 2024-05-07 |  |  | LOOP 0 | T0975CA | 2024-06-17T16:45:49.28+00:00 | David Wolny | [8 empty] | Design
|  | 286830 | WPI | P2 | IE | Prasad Madali | The accessibility of the I-shaft provides an ergo risk to the operators in chassis. The posture in order to access this joint leaves the operator in a poor posture position. Reviewed with the VA ergonomist but still needs to be re-scrolled or elements split up between different job stations. | Chassis Blank | ChassisBlank | Digital Scroll |  | Pending |  | 2024-03-27 08:07 | 2024-03-27 07:29 | Scroll still in progress for chassis | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2024-08-14 |  |  |  | Chassis 1 |  |  | 36 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 58 | 2024-08-14 |  |  | LOOP 0 | T2851AD | 2024-05-24T13:25:46.467+00:00 | Anthony Dinardo | [8 empty] | Method
|  | 287006 | WPI | P2 | VPE Tooling | Mark Storace | Harness heater not on the layout. Will we be getting an oven. Size, does it change the footprint? Funded? power in location, ceramic tiles required for additional parts, has not been turned on, what is the temp we want harness to get to? Validate it works before being shipped to BAP. | Trim Blank | TrimBlank | WPI Layout Review | 5/27/24 Validation is normal process. These are questions, not issues. Please close. 5/22/24 Discussed at 5/22/24 meeting, station layout shall be reviewed during the station design phase. This is normal process, not an issue. Please close. | Pending |  | 2024-04-02 14:38 | 2024-04-02 13:08 | Discussed at 5/22/24 meeting, station layout shall be reviewed during the station design phase. This is normal process, not an issue. Please close. | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2024-05-22 |  |  |  | Trim 1 |  |  | 46 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 46 | 2024-05-22 |  |  | LOOP 0 | T2167MS | 2024-05-27T12:01:31.543+00:00 | Anthony Dinardo | [8 empty] | Machine
|  | 287235 | WPI | P2 | VPE Paint | Michael Wallace | Accommodation of Tutone masking on a moving line, pending ergonomic study. | Paint Blank | PAINTBlank | WPI Layout Review | Countermeasure being either, i) installation of a roller table to create a stop station in place of the moving line, or ii) overhead gantry to assist with masking process on a moving line | Pending |  | 2024-04-08 11:17 | 2024-04-08 12:15 | PO has been issued, awaiting approval on prototype of WL table. Pending end of August 2024 | [8 empty] | 0 | [5 empty] | 0 | Paint | Pending validation | 2024-08-31 |  |  |  | Paint 1 |  |  | 56 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 60 | 2024-08-31 |  |  | LOOP 0 | T3172SP | 2024-07-29T12:54:35.683+00:00 | Jacob Slota | [8 empty] | Method
|  | 287264 | WPI | P2 | VPE BIW | Omar Malik | Right fender install process: Ergo Risk. Safety and VR sim to determine actual height. 4/19/2024 - Joe DZ shared updated VR sim data for 95th percentile. Will follow up with 25th percentile data. VR sim verified fender load is within Ergo Guidelines. Securing the upper inner fasteners on the loadbeam is a blind operation and the 4 lower fasteners cause the operator to squat. Safety risk has been identified when securing the 2 fasteners in the wheelhouse as the operator is crouching while walking with the car to secure these fasteners. 4/4/2024 - Safety and VR sim to determine actual height. Verify height is within ergo guidelines. Reaching over 1300mm is outside the golden zone. Shoulder not in optimal position to secure 5 upper fasteners. | BIW Blank | BIWBlank | 2D Layout Review | 6/17/24: issue reviewed with Launch team (plant and VPE) - compressing panel line will close this issue, decision on panel line compression to be made soon. 4/19/2024 - Joe DZ shared updated VR sim data for 95th percentile. Will follow up with 25th percentile data. VR sim verified fender load is within Ergo Guidelines. Securing the upper inner fasteners on the loadbeam is a blind operation and the 4 lower fasteners cause the operator to squat. Safety risk has been identified when securing the 2 fasteners in the wheelhouse as the operator is crouching while walking with the car to secure these fasteners. 4/4/2024 - Safety and VR sim to determine actual height. Verify height is within ergo guidelines. Reaching over 1300mm is outside the golden zone. Shoulder not in optimal position to secure 5 upper fasteners. | Pending |  | 2024-04-09 13:05 | 2024-04-09 12:45 | panel line compression will solve this issue - waiting for plan to be approved | [8 empty] | 0 | [5 empty] | 0 | BIW | Pending validation | 2024-07-15 |  |  |  | Body 1 |  |  | 61 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 54 | 2024-07-15 |  |  | LOOP 0 | T0975CA | 2024-07-15T16:53:42.043+00:00 | Chris Aitchison | [8 empty] | Method
|  | 287409 | WPI | P3 | Chassis | Diana Tan | Organize hourly training for launch team with CTC for battery Build. | Chassis Blank | ChassisBlank | Process Sheet Review | Ongoing conversations regarding this, but this is dependent on whether we are building battery at BAP for X1 which will push this task back or if needed for pilot we will do this task sooner. | Pending |  | 2024-04-11 11:50 | 2024-04-11 12:45 | On going meeting with CTC to organize this. Weekly meeting are in place. | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2025-02-01 |  |  |  | Chassis 1 |  |  | 67 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 82 | 2025-02-01 |  |  | LOOP 0 | T1766AG | 2024-05-01T12:16:18.243+00:00 | Abillan Gnanavel | [8 empty] | Method
|  | 287410 | WPI | P2 | Safety | Klaus Ohrnberger | Cost and Build of quarantine area for battery build - to be updated with time expected for this to be built | Chassis Blank | ChassisBlank | Build Issue | Klaus'' group have identified locations for where quarantine areas can be. Waiting on completion during the construction process. | Pending |  | 2024-04-11 12:05 | 2024-04-11 12:48 | On going layout meeting are taking place, these meeting dictate where the quarantine area will be. We are confirmed to have one, but ongoing meeting change location of this. This will be required prior to launch. | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2025-02-03 |  |  |  | Chassis 1 |  |  | 68 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 83 | 2025-02-03 |  |  | LOOP 0 | T1766AG | 2024-05-01T12:17:34.03+00:00 | Abillan Gnanavel | [8 empty] | Method
|  | 287413 | WPI | P3 | Safety | Gregory Bain | Creation of JSRA / Training documents required for Battery Build Employees | Chassis Blank | ChassisBlank | Build Issue | This will be done during pilot build as while the launch team builds the car they will also create the documents as well. | Pending |  | 2024-04-11 13:41 | 2024-04-11 12:51 | JSRA's will be completed by the battery launch team with assistance from Supervisors, TL, and WHS during pilot build in our MTA once established. | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2024-11-29 |  |  |  | Chassis 1 |  |  | 71 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 73 | 2024-11-29 |  |  | LOOP 0 | T1766AG | 2024-05-01T12:18:01.623+00:00 | Abillan Gnanavel | [8 empty] | Method
|  | 287419 | WPI | P2 | Safety | Gregory Bain | Need a plan for heat stress due to heat in Arc Suit PPE -- plan on heat reliefs / rotation of EE to not delay mainline throughput at 35 JPH while battery cell works at 17 JPH/ | Chassis Blank | ChassisBlank | Build Issue | PPE has been finalized from the incident energy calculations, PPE heat breaks to be discussed closer to launch. | Pending |  | 2024-04-11 12:19 | 2024-04-11 13:00 | This is a long term item, not due until X3 build. Corporate Industrial Hygiene is providing assistance based on similar concerns at WAP. | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2025-04-25 |  |  |  | Chassis 1 |  |  | 77 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 94 | 2025-04-25 |  |  | LOOP 0 | T1766AG | 2024-05-01T12:19:38.923+00:00 | Abillan Gnanavel | [8 empty] | Man
|  | 288085 | WPI | P2 | VPE Process | John Seminerio | Stations need to be re-numbered and added to finalized layout in order for ILE to determine PUP (part usage point) for Material Systems Setup (MT27, Material Routing, Kanban, etc.) | Trim Blank | TrimBlank | Digital Scroll | 6/11/24 - (B.Keeler) Kick off meeting initiated 6/10. Follow up meeting scheduled for week of 6/17, with conveyor group in attendance. Usage points will need to be redefined in each center starting with BIW and Paint due to re-tool/addition of new systems, compression, etc. in each center. Usage points cannot be redefined without a finalized layout and scroll with new station numbers. | Pending |  | 2024-04-24 14:56 | 2024-04-24 09:48 | station id numbers to be updated to new scroll and reflected on the shop floor with proper signage | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2024-09-30 |  |  |  | Trim 1 |  |  | 107 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE | IE |  | 65 | 2024-09-30 |  |  | LOOP 0 | T9200BK | 2024-06-14T10:42:12.407+00:00 | Brittany Keeler | [8 empty] | Material
|  | 288086 | WPI | P3 | VPE IE | Vincent Vu | ILE needs list of all production tooling (ex. decklid blocks) and/or ISD protection (ex. sill protectors), with install and removal stations that will be required to be moved around GA by MLM | Trim Blank | TrimBlank | Digital Scroll | 6/18/24 - (B.Keeler) MLM is aware of Paint tooling scrolled to Trim, and Strut cones scrolled to Pallet. Unknown what ISD/Tooling items remain to be scrolled. 5/27/2024 - (Vincent V.) Wendell has been notified to begin the process of performing a risk assessment in order to identify required ISD and accompanying station. 5/14/2024 - (Vincent V.) IE department requires information from tooling and ISD teams in order to scroll activities 04/24/2024 - (B.Keeler) This information is required for internal Rack Designs and for creating MLM circles of work | Pending |  | 2024-04-24 14:55 | 2024-04-24 10:46 | 7/3/2024 (B.Keeler) - Trim 1/2 scroll targeted to be completed by September first, required information to be available at scroll completion date. | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2024-07-03 |  |  |  | Trim 1 |  | Prasad Madali | 108 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE | VPE IE |  | 52 | 2024-07-03 |  |  | LOOP 0 | T9200BK | 2024-07-03T10:58:17.413+00:00 | Brittany Keeler | [8 empty] | Machine
|  | 288203 | WPI | P2 | VPE Process | Elizabeth Lekarczyk | How are the rear seats being loaded to the vehicle for J4U? Will it be an ergo arm or manual operation? If it is a manual operation will need an ergo assessment completed for this element. | Final Blank | FinalBlank | Digital Scroll | 5/1 A Bozick: The rear seat is coming to the line in three pieces. The 60% seat back, the 40% seat back, and the seat cushion. Based on the weights. We are planning on having an arm for the left backrest, but that is all pending an ergo study. Exact design is not known yet. 2024/06/30 - - [Issue Reopened] The Issue has not been closed, RMS will Force Issue Open Automatically. | Pending |  | 2024-05-16 14:07 | 2024-04-30 09:33 | Exact design not known yet. Waiting to nail down how seat delivered to the line and how seats will look on delivery pallet | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2024-08-30 |  |  |  | Final 1 |  |  | 111 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 60 | 2024-06-30 |  |  | LOOP 0 | T2851AD | 2024-07-09T11:27:46.837+00:00 | Anthony Dinardo | [8 empty] | Method
|  | 288207 | WPI | P2 | VPE BIW | Omar Malik | Left Front and Rear Door Install Operator is required to bend more than 40 degrees to secure the lower bolt on the lower hinge. This task violates the Stellantis Ergo Guidelines. | BIW Blank | BIWBlank | 2D Layout Review | 7/15: Panel line compression will resolve ergo issues - final approval for panel line pending 4/19/2024 - Joe DZ shared updated VR sim for 95th percentile. Will follow up with 25th percentile. Securing the lower fastener on the lower hinge causes operator to bend beyond 40 degrees which violates Stellantis Ergo Guidelines. 4/11/2024 - Met with Joe DZ (VR Specialist) and Safety to determine actual height. Data not matching CAD. 4/4/2024 - Safety and VR sim to determine actual height. Bending beyond 40 degrees unacceptable position for repetitive work. | Pending |  | 2024-04-30 14:38 | 2024-04-30 10:47 | I fpanel line is compressed ergo issue will be resolved | [8 empty] | 0 | [5 empty] | 0 | BIW | Pending validation | 2024-07-15 |  |  |  | Body 1 |  |  | 114 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE | VPE BIW |  | 54 | 2024-07-15 |  |  | LOOP 0 | T0975CA | 2024-07-15T16:55:14.327+00:00 | Tracy Oldford | [8 empty] | Method
|  | 288208 | WPI | P2 | VPE BIW | Omar Malik | Left Fender Install: Loose installing the lower 2 fasteners on the dog leg at Fender Install on 18-3. This will require the operator to squat/kneel while performing this task. This is a forbidden posture (Stellantis Ergo Guidelines). | BIW Blank | BIWBlank | 2D Layout Review | 7/15/24: panel line compression will resolve ergo issues - waiting for final approval for panel line compression 4/19/2024 - Joe DZ shared updated VR sim data for 905th percentile. Will follow up with 25th percentile. VR sim verified the 2 lower dog leg fasteners violate the Ergo Guidelines. 4/4/2024 - Safety and VR sim to determine actual height. Verify height is within ergo guidelines. Securing 4 lower fasteners require operator to kneel which is not permitted. | Pending |  | 2024-04-30 14:37 | 2024-04-30 11:11 | panel line compression will resolve ergo issues - waiting for final approval for panel line compression | [8 empty] | 0 | [5 empty] | 0 | BIW | Pending validation | 2024-07-15 |  |  |  | Body 1 |  |  | 115 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE | VPE BIW |  | 54 | 2024-07-15 |  |  | LOOP 0 | T0975CA | 2024-07-15T16:56:37.343+00:00 | Tracy Oldford | [8 empty] | Method
|  | 288209 | WPI | P3 | VPE BIW | Omar Malik | Left Front and Rear Door Hinge Install. 4/19/2024 - front door is 1107.01mm / 43.58" long. 18-3 deck is 125" wide. No info in rack depth yet. Adding +5" for rack depth, and 5" extra on door length for depth of roller table, for a total of 91.16". Width of the car is 6'. This provides the operator with roughly 22" of useable working space. Anything less than 20" is considered a pinch point. There are 2 different deck depth on 18-3. 141" and 125". Waiting on rack sizes from MLM. 4/4/2024 - Pinch Point may be created when door is on the roller rack. Operator must have a minimum 20"/508cm. | BIW Blank | BIWBlank | 2D Layout Review | 7/15/24: panel line compression will allow more flexability in station layout - waiting on final approval for compression 4/19/2024 - front door is 1107.01mm / 43.58" long. 18-3 deck is 125" wide. No info in rack depth yet. Adding +5" for rack depth, and 5" extra on door length for depth of roller table, for a total of 91.16". Width of the car is 6'. This provides the operator with roughly 22" of useable working space. Anything less than 20" is considered a pinch point. There are 2 different deck depth on 18-3. 141" and 125". Waiting on rack sizes from MLM. 4/4/2024 - Pinch Point may be created when door is on the roller rack. Operator must have a minimum 20"/508cm. | Pending |  | 2024-04-30 14:37 | 2024-04-30 11:25 | panel line compression will allow more flexability in station layout - waiting on final approval for compression | [8 empty] | 0 | [5 empty] | 0 | BIW | Pending validation | 2024-07-15 |  |  |  | Body 1 |  |  | 116 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE | VPE BIW |  | 54 | 2024-07-15 |  |  | LOOP 0 | T0975CA | 2024-07-15T16:57:34.387+00:00 | Tracy Oldford | [8 empty] | Method
|  | 288210 | WPI | P2 | VPE BIW | Omar Malik | Hood Install: Installing hood will require operator to reach too far over their shoulder which violates the Stellantis Ergo Guidelines. | BIW Blank | BIWBlank | 2D Layout Review | 7/15/24: panel line compression would resolve this ergo issue - waiting for final approval for compression 4/19/2024 - line height will impact installation of hood. Fixture is secured to car and hood is installed from front. Due to height, hood will need to be installed from RH side. Height will be over operator's shoulders. | Pending |  | 2024-04-30 14:36 | 2024-04-30 11:34 | panel line compression would resolve this ergo issue - waiting for final approval for compression | [8 empty] | 0 | [5 empty] | 0 | BIW | Pending validation | 2024-07-15 |  |  |  | Body 1 |  |  | 117 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE | VPE BIW |  | 54 | 2024-07-15 |  |  | LOOP 0 | T0975CA | 2024-07-15T16:58:27.447+00:00 | Tracy Oldford | [8 empty] | Method
|  | 288211 | WPI | P2 | VPE BIW | Omar Malik | Decking on 19-1A will need to be leveled to meet height at Right Front Door Install. Currently there are 2 different floor heights and 2 ramps. | BIW Blank | BIWBlank | 2D Layout Review | 7/15/24: panel line compression will resolve issue - waiting for final approval for compression Level out the decking on 19-1A to meet the height at Right Front Door Install. | Pending |  | 2024-04-30 14:35 | 2024-04-30 11:39 | panel line compression will resolve issue - waiting for final approval for this plan | [8 empty] | 0 | [5 empty] | 0 | BIW | Pending validation | 2024-07-15 |  |  |  | Body 1 |  |  | 118 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE | VPE BIW |  | 54 | 2024-07-15 |  |  | LOOP 0 | T0975CA | 2024-07-15T16:45:40.2+00:00 | Tracy Oldford | [8 empty] | Design
|  | 288318 | WPI | P3 | VPE Facilities | Ravdeep Khokhar | Station 2235 on chassis 1 end of the brake deck needs to be modified. | Chassis Blank | ChassisBlank | Digital Scroll | IE wants this to be a workable station with content, it is currently a knee pit and requires to be raised or filled for work accessibility. > Ravdeep K: As per IE's, scroll has not matured yet so we are awaiting final scroll layout to determine what height to make this station (floor level, or extend the deck). 2024/07/24 - - [Issue Reopened] The Issue has not been closed, RMS will Force Issue Open Automatically. | Pending |  | 2024-05-03 11:26 | 2024-05-03 10:46 | Waiting for completed scroll for chassis | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2024-08-14 |  |  |  | Chassis 1 |  |  | 128 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 58 | 2024-07-24 |  |  | LOOP 0 | T2851AD | 2024-07-24T11:42:42.467+00:00 | Anthony Dinardo | [8 empty] | Design
|  | 288322 | WPI | P2 | ILE | Dhruv Devichand | Is the supplier able to keep up with the line rate for the liftgate? | Trim Blank | TrimBlank | 2D Layout Review | Will they make it for the broadcast window time frame at the beginning of trim? 2024/07/10 - - [Issue Reopened] The Issue has not been closed, RMS will Force Issue Open Automatically. | Pending |  | 2024-05-03 11:28 | 2024-05-03 11:05 | Liftgate Sourcing | [8 empty] | 0 | [5 empty] | 0 | GA | Pending validation | 2024-08-30 |  |  |  | Trim 1 |  |  | 132 | [6 empty] | FALSE |  | FALSE | FALSE | FALSE |  |  | 60 | 2024-07-10 |  |  | LOOP 0 | T2851AD | 2024-07-10T12:13:09.653+00:00 | Anthony Dinardo | [8 empty] | Material